Third meeting of the Mediterranean Wetlands Committee
Djerba, Tunisia, 1 - 5 April 2000 


Table 2: MedWet Team activities 1999-2000 
	Action
	Objectives
	Focal organisation
	Time frame
	Budget 

Funding
	Status

	MedWet web site
	Wider communication on Mediterranean wetlands
	EKBY
	1999-2001
	EUR 23500 

Greek Govt.
	Being restructured

	MedWet address database
	Contact possibilities with wider network
	EKBY
	1997-2001
	EUR 6000 

Greek Govt.
	Need of filtering and completion

	MedWet/Com3  

organisation
	Planning, logistics, preparation and dissemination of working documents
	MedWet Team + DGF
	Oct. 1999 – March 2000
	 
	Almost completed

	Review of the MedWet Team
	Evaluation of the operation and of the work of the MedWet Team
	B. Phillips 

Ramsar
	Sept. 1999 – Jan. 2000
	 
	Review completed and distributed to all MedWet/Com members

	MedWet archive
	Preparation of a CD-ROM with all key MedWet and MedWet/Com documents 1991-2000
	MW/C
	2000
	 
	Main documents being collected in electronic form

	MedWet logo
	Legal protection of the MedWet + MedWet/Com title and logo
	MW/C, J.-P. Taris 

Tour du Valat
	1999-2000
	 
	In progress

	Reporting system
	Development of a system for monitoring and reporting on all MedWet activities
	MW/C, EKBY
	1999-2000
	EUR 6000 

Greek Govt.
	System almost completed


